Annex A															EDRM: 2149362

| PROJECT TITLE | Community-Led Infrastructure Finance Facility: June 2009 – March 2014 |
| --- | --- |
| GOAL | Indicator | Baseline | Milestone 2010 | Milestone 2012 | Target2014 |  |
| Reduce poverty by increasing the access of slum dwellers to public, private and civil society sector resources for housing and basic services delivery. | For MDG 7, Target 10: (a) Indicator 7.8 - Proportion of population using an improved drinking water source; and (b) Indicator 7.9 - Proportion of population using an improved sanitation facility | (a) 87%* (b) 62%* | (a) 87.4% (b) 62.3% | (a) 88.5% (b) 63% | (a) 89%** (b) 63.4%** |  |
|  |  | Source |  |
|  |  | UNICEF/WHO Joint Monitoring Programme (JMP) and 2008 UN MDG Report. *Figures are based on data from 2006. ** The 2014 target is partly based on historical trends of 2.5% for water and 2% for sanitation, but has been conservatively lowered due to likely impacts of the global financial crisis. |  |
|  | Indicator | Baseline | Milestone 2010 | Milestone 2012 | Target 2014 |  |
|  | For MDG 7, Target 11: Indicator 7.10 - Proportion of urban population living in slums | 36.5%* | 35.9% | 34.7% | 33.6%** |  |
|  |  | Source |  |
|  |  | 2008 UN MDG Report * Baseline figure is based on data from 2005. ** Estimates based on 1.6% reduction per year (average of 1990-2005 trend). |  |
| PURPOSE | Indicator | Baseline Mar 2009 | Milestone 1 Mar 2011 | Milestone 2 Mar 2013 | Target Mar 2014 | Assumptions |
| Enable organisations of the urban poor to access greater public, private and civil society sector resources to deliver adequate and sustainable housing and basic services for slum dwellers through innovative practice and influence on policy. | Organisations of the urban poor supported by CLIFF developed the capacity required to access greater public, private and civil society sector resources, particularly in terms of: (a) Improved capacity (b) Accessing finance | (a) 1 (b) 1 | (a) 5 (b) 3 | (a) 6 (b) 5 | (a) At least 6 (b) At least 6 | That enabling organisations of the urban poor to access greater public, private and civil society sector resources will reduce poverty. That a modification in relevant policies and practices will lead to a reduction in poverty. Homeless International will contribute through access to its Guarantee Fund (currently £0.7m.) and Africa Bond (currently in excess of £0.1m.) |
|  |  | Source |  |
|  |  | Mid-Term Evaluation End of Project Evaluation |  |
|  | Indicator | Baseline Mar 2009 | Milestone 1 Mar 2011 | Milestone 2 Mar 2013 | Target Mar 2014 |  |
|  | Participating countries modified policies and practices to provide greater resources towards the delivery of adequate and sustainable housing and basic services for slum dwellers. | 1 | 3 | 5 | At least 5 |  |
|  |  | Source |  |
|  |  | Mid-Term Evaluation End of Project Evaluation |  |
| INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |
|  | £15 million | Nil | £0.8 million* £3.75 million** | £19.55 million | 77% |
| INPUTS (HR) | DFID (FTEs) | Based on the latest cashflows of the CLIFF-supported project portfolio it is projected that existing IPs will contributed £12 million in terms of revolving capital over the next 5-15 years. The non-financial contribution communities are making towards CLIFF should not be under-valued. Communities contribute their time to a range of activities: meetings with government bodies relating to projects; designing projects; and, supervision of construction. In some housing projects across the three IPs, communities provide ‘sweat equity’ to the construction of projects. * Homeless International Guarantee Fund and Africa Bond ** Possible SIDA contribution (logframe to be updated once confirmed) |
|  | 0.2 |  |

| OUTPUT 1 | Indicator | Baseline Mar 2009 | Milestone Mar 2011 | Milestone 2 Mar 2013 | Target Mar 2014 | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| CLIFF implementation expanded through establishment of new Implementing Partners (IPs) in current and additional participating countries. | Number of new IPs established in current and additional participating countries. | 0 IPs | 2 IPs | 3 IPs | At least 3 IPs | That DFID funding will begin to flow no later than July 2009. |
|  |  | Source |  |
|  |  | Partnership Agreements formalised between new IPs and Coordinating Partner (CP). |  |
| IMPACT WEIGHTING |  |  |  |
| 16% |  |  |  |
|  |  |  | RISK RATING |
|  |  |  | MEDIUM |

| OUTPUT 2 | Indicator | Baseline Mar 2009 | Milestone 1 Mar 2011 | Milestone 2 Mar 2013 | Target: Mar 2014 | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Capacity and reputation of existing and new IPs strengthened to access greater public, private and civil society sector resources to deliver adequate and sustainable housing and basic services for slum dwellers through innovative practice and influence on policy. | IPs made good progress towards addressing capacity shortfalls in key areas in line with Fiduciary Action Plans and Annual CLIFF Business Plans. | 0 IPs | 4 IPs | 6 IPs | At least 6 IPs | That current and potential IPs are willing to enhance their capacity to the extent and in the way required by relevant organisations within the public and private sectors, especially financial institutions. That enhanced capacity will lead to an increase in reputation and credit rating when viewed by relevant organisations and departments in the public, private and civil society sector, especially financial institutions. |
|  |  | Source |  |
|  |  | Fiduciary Assessment and Monitoring Visit reports, including Fiduciary Action Plans. Annual audit reports (including management letter). Project reports and documentation, including plans and Cashflows. Six-monthly Monitoring Reports. Annual CLIFF Business Plans and Budgets. |  |
|  | Indicator | Baseline Mar 2009 | Milestone Mar 2011 | Milestone Mar 2013 | Target Mar 2014 |  |
|  | Formal recognition of IPs ability to innovate and deliver adequate and sustainable housing and basic services projects by relevant public, private and civil society bodies. | 1 IPs | 4 IPs | 5 IPs | At least 6 IPs |  |
|  |  | Source |  |
|  |  | Monitoring Visit reports. Formal agreements and intentions from the public, private or civil society sectors to work with IPs (e.g. contracts, serving on government advisory groups, loan agreements with financial institutions, land allocation agreements with private land owners, joint ventures with commercial developers). Reports of progress under formal agreements, commitments and intentions from public and private institutions. Credit rating from appropriate institutions. Six-monthly Monitoring Reports. Records of awards, media coverage, interviews etc. |  |
| IMPACT WEIGHTING |  |  |  |
| 16% |  |  |  |
|  |  |  | RISK RATING |
|  |  |  | MEDIUM |

| OUTPUT 3 | Indicator | Baseline Mar 2009 | Milestone 1 Mar 2011 | Milestone 2 Mar 2013 | Target Mar 2014 | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Mobilisation, leverage and blending of financial (e.g. cost recovery, loan finance, construction contractor investment) and non-financial (e.g. land, basic services, technical skills) resources from the public and private sectors, as well as from community contributions, for the delivery of adequate and sustainable housing and basic services for slum dwellers. | IPs established effective partnerships with relevant organisations and departments in the public and private sectors. | 3 IPs | 4 IPs | 5 IPs | At least 6 IPs | That local policy environments and conditions do not obstruct the required mobilisation, leverage and blending of resources from the public sector. That local business environments and conditions do not obstruct the required mobilisation, leverage and blending of resources from the private sector. That the financial crisis will not significantly constrain resource mobilisation. That significant non-monetary resources will also be mobilised and leveraged in the form of skilled and unskilled inputs etc. |
|  |  | Source |  |
|  |  | Project documentation, including plans and cash flow forecasts. Formal agreements, commitments and intentions from the public or private sectors to provide resources. Six-monthly Monitoring Reports. |  |
|  | Indicator | Baseline Mar 2009 | Milestone 1 Mar 2011 | Milestone 2 Mar 2013 | Target Mar 2014 |  |
|  | Actual and projected value of cost recovery (e.g. cash subsidies, government contract payments, fungible development rights) mobilised by approved CLIFF-supported projects from public and private sectors. | £43.2 million | £2.8 million + Baseline | £10.6 million + Baseline | At least £14 million + Baseline |  |
|  |  | Source |  |
|  |  | Formal agreements, commitments and intentions from the public or private sectors to provide resources. Project documentation, including plans and cash flow forecasts Six-monthly Monitoring Reports. |  |
|  | Indicator | Baseline Mar 2009 | Milestone 1 Mar 2011 | Milestone 2 Mar 2013 | Target Mar 2014 |  |
|  | Actual and projected value of external loan finance mobilised and leveraged by approved CLIFF-supported projects. | £5.3 million | £0.5 million + Baseline | £1.8 million + Baseline | At least £2.4 million+ Baseline |  |
|  |  | Source |  |
|  |  | Formal agreements, commitments and intentions from the public or private sector to provide loans. Project documentation, including plans and cash flow forecasts Six-monthly Monitoring Reports. |  |
|  | Indicator | Baseline Mar 2009 | Milestone 1 Mar 2011 | Milestone 2 Mar 2013 | Target Mar 2014 |  |
|  | Actual and projected value of cost recovery mobilised from households by approved CLIFF-supported projects. | £0.9 million | £2 million + Baseline | £7.7 million + Baseline | At least £10 million + Baseline |  |
|  |  | Source |  |
|  |  | Formal agreements, commitments and intentions from households/communities to contribute towards the cost of their housing and basic services or pay rent. Project documentation, including plans and cash flow forecasts Six-monthly Monitoring Reports. |  |
| IMPACT WEIGHTING | Indicator | Baseline Mar 2009 | Milestone 1 Mar 2011 | Milestone 2 Mar 2013 | Target Mar 2014 |  |
| 16% | Actual and projected area of land mobilised by approved CLIFF-supported projects from public and private sectors. | 20.6 Hectares | 5 Hectares + Baseline | 19 Hectares + Baseline | At least 25 Hectares + Baseline |  |
|  |  | Source | RISK RATING |
|  |  | Formal agreements, commitments and intentions from the public or private sector to contribute land. Project documentation, including plans and cash flow forecasts Six-monthly Monitoring Reports. | HIGH |

| OUTPUT 4 | Indicator | Baseline Mar 2009 | Milestone Mar 201 | Milestone Mar 2013 | Target Mar 2014 | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Adequate and sustainable housing and basic services solutions developed as a result of CLIFF. | Number of adequate and sustainable housing units constructed/being constructed for slum dwellers as a result of CLIFF. | 5,673 | 1,142 + Baseline | 4,340 + Baseline | At least 5,710 + Baseline | That adequate and sustainable housing and basic services solutions can be innovated and delivered by slum dwellers. That delivery achieved by IPs continues, on average, at least at the level achieved during the previous phase of CLIFF. |
|  |  | Source |  |
|  |  | Six-monthly Monitoring Reports. Project documentation. Annual reports. |  |
|  | Indicator | Baseline Mar 2009 | Milestone Mar 2011 | Milestone Mar 2013 | Target Mar 2014 |  |
|  | Number of basic services constructed/being constructed for slum dweller families as a result of CLIFF. | 14,648 | 4,455 + Baseline | 16,928 + Baseline | At least 22,273 + Baseline |  |
|  |  | Source |  |
|  |  | Six-monthly Monitoring Reports. Project documentation. Annual reports. |  |
|  | Indicator | Baseline Mar 2009 | Milestone Mar 2011 | Milestone Mar 2013 | Target Mar 2014 |  |
|  | Number of slum dwellers benefiting and projected to benefit from adequate and sustainable housing as a result of CLIFF. | 28,365 | 5,710 + Baseline | 21,700 + Baseline | At least 28,552 + Baseline |  |
|  |  | Source |  |
|  |  | Six-monthly Monitoring Reports. Project documentation. Annual reports. |  |
| IMPACT WEIGHTING | Indicator | Baseline Mar 2009 | Milestone Mar 2011 | Milestone Mar 2013 | Target Mar 2014 |  |
| 20% | Number of slum dwellers benefiting and projected to benefit from basic services as a result of CLIFF. | 732,400 | 88,358 + Baseline | 335,760 + Baseline | At least 441,789 + Baseline |  |
|  |  | Source | RISK RATING |
|  |  | Six-monthly Monitoring Reports. Project documentation. Annual reports. | MEDIUM |

| OUTPUT 5 | Indicator | Baseline Mar 2009 | Milestone Mar 2011 | Milestone Mar 2013 | Target Mar 2014 | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Changes to the policies and practices of relevant bodies in each country where CLIFF being implemented which relate to the delivery of adequate and sustainable housing and basic services for slum dwellers. | Number of countries with new effective changes in the policies and practices of relevant bodies in the public sector. | 0 | 3 | 5 | At least 5 | That changes in policy and practice will facilitate broader based participation of organisations of the urban poor in housing and basic services delivery for slum dwellers. CLIFF will be coordinated with programmes supported by DFID-India office and Federal and State governments in India. Similar opportunities will be sought for coordinating with other agencies which support relevant programmes in participating countries. |
|  |  | Source |  |
|  |  | National and local government policy documents. Six-monthly Monitoring Reports. |  |
|  | Indicator | Baseline Mar 2009 | Milestone Mar 2011 | Milestone Mar 2013 | Target Mar 2014 |  |
|  | Number of countries with new effective changes in the policies and practices of relevant bodies in the private and civil society sectors. | 0 | 3 | 5 | At least 5 |  |
|  |  | Source |  |
|  |  | Private sector investment plans and practices. Six-monthly Monitoring Reports. |  |
| IMPACT WEIGHTING |  |  |  |
| 16% |  |  |  |
|  |  |  | RISK RATING |
|  |  |  | MEDIUM |

| OUTPUT 6 | Indicator | Baseline Mar 2009 | Milestone Mar 2010 | Milestone Mar 2013 | Target Mar 2014 | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Knowledge, learning and good practice emerging from CLIFF (pertaining to Outputs 1 - 5 above) documented, disseminated and used to advocate. | Key emerging lessons from CLIFF implementation being captured and documented by all Stakeholders. |  | Communications Strategy for CLIFF in place and being implemented | To be defined in Communications Strategy | To be defined in Communications Strategy | That documenting and disseminating knowledge and learning will mainstream good practice will lead to the desired changes in policy and practice. That Cities Alliance and other partners will actively contribute to the output. |
|  |  | Source |  |
|  |  | Project documentation. Six-monthly Monitoring Reports. Annual reports. Stakeholder communications. Reflection, Learning and Planning (RLP) event including documentation. References to CLIFF material in reputable reports. Website access to CLIFF knowledge base. International fora. Sources identified in Communications Strategy. |  |
| IMPACT WEIGHTING | Indicator | Baseline Mar 2009 | Milestone Mar 2010 | Milestone Mar 2013 | Target Mar 2014 |  |
| 16% | Key emerging lessons documented being disseminated and used to advocate for changes to the policies and practices of a range of relevant bodies in the public, private and civil society sectors, by all Stakeholders. |  | Communications Strategy for CLIFF in place and being implemented | To be defined in Communications Strategy | To be defined in Communications Strategy |  |
|  |  | Source | RISK RATING |
|  |  | Project documentation. Six-monthly Monitoring Reports. Annual reports. Stakeholder communications. RLP event including documentation. References to CLIFF material in reputable reports. Website access to CLIFF knowledge base. International fora. Sources identified in Communications Strategy. | MEDIUM |

## Activities Log

| OUTPUTS 2-6 | ACTIVITY 1.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer |
| --- | --- | --- | --- | --- | --- | --- |
| Implementing Partners (IPs) | Produce and implement Annual CLIFF Business Plans and Budgets | Annually | Annually | Annually | Models to provide housing and basic services that are both adequate and sustainable for slum dwellers may not be developed in each country where CLIFF is active The models developed and demonstrated through CLIFF may not be replicated at scale by others There may not be sufficient mobilisation, leverage and blending of resources from the public or private sectors IPs may not have capacity to significantly increase activity in response to increased demand arising from their enhanced reputation and credit rating Necessary pro-poor changes in policy and practice may not be stimulated by CLIFF demonstrations IPs may not submit sufficient requests which meet the agreed Capital Grant Criteria IPs may not strengthen their capacity for effective implementation and accountability to the extent required by public and private sector organisations, especially financial institutions Enhanced capacity may not lead to an increase in reputation and credit rating when viewed by public and private sector organisations, especially financial institutions The emerging global financial crisis may limit CLIFF projects by constraining the availability of community, public and private resources | GFDD Staff |
|  | ACTIVITY 1.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Communicate regularly with CP and FCP, and as required with FPs, to discuss progress and fulfil contractual requirements under CLIFF | Regularly | Regularly | Regularly |  | GFDD Staff |
|  | ACTIVITY 1.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support visits made or organised by Stakeholders | As required (but obviously within reason) | As required (but obviously within reason) | As required (but obviously within reason) |  | GFDD Staff |
|  | ACTIVITY 1.4 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Submit Capital Grant Requests to CP for appraisal, based on demand | As required | As required | As required |  | GFDD Staff |
|  | ACTIVITY 1.5 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Submit financial reports to CP on a timely basis | As required, and at least on a quarterly basis | As required, and at least on a quarterly basis | As required, and at least on a quarterly basis |  | GFDD Staff |
|  | ACTIVITY 1.6 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Submit annual external audits and management letters (for both the CLIFF project and the organisation) to CP on a timely basis | Annually | Annually | Annually |  | GFDD Staff |
|  | ACTIVITY 1.7 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support development and delivery of the Communications Strategy | Regularly | Regularly | Regularly |  | GFDD Staff |
|  | ACTIVITY 1.8 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Co-ordinate RLP Events where required, in conjunction with CP, and participate | As required | As required | As required |  | GFDD Staff |
|  | ACTIVITY 1.9 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support efforts to raise additional funding for CLIFF, if effective demand is demonstrated | As required | As required | As required |  | GFDD Staff |
|  | ACTIVITY 1.10 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Participate in CSB meetings | Six-monthly | Six-monthly | Six-monthly |  | GFDD Staff |
|  | ACTIVITY 1.11 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Report on CLIFF progress to own governance structures and ensure related decisions are made on a timely basis | Regularly | Regularly | Regularly |  | GFDD Staff |

| OUTPUTS 1-6 | ACTIVITY 2.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer |
| --- | --- | --- | --- | --- | --- | --- |
| Co-ordinating Partner (CP) | Assess potential new IPs against Context and IP Criteria, and consult CSB with recommendations as to whether to enter new partnership | As required to reach target of 1 in 2009/10 | As required to reach target of 1 in 2010/11 | As required to reach target of 1 in 2011/12 | Insufficient locations and organisations may be identified which meet the agreed Context Criteria and IP Criteria The models developed and demonstrated through CLIFF may not be replicated at scale by others There may not be sufficient mobilisation, leverage and blending of resources from the public or private sectors IPs may not have capacity to significantly increase activity in response to increased demand arising from their enhanced reputation and credit rating Necessary pro-poor changes in policy and practice may not be stimulated by CLIFF demonstrations IPs may not submit sufficient requests which meet the agreed Capital Grant Criteria IPs may not strengthen their capacity for effective implementation and accountability to the extent required by public and private sector organisations, especially financial institutions Enhanced capacity may not lead to an increase in reputation and credit rating when viewed by public and private sector organisations, especially financial institutions The emerging global financial crisis may limit CLIFF projects by constraining the availability of community, public and private resources | GFDD Staff |
|  | ACTIVITY 2.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support new IPs with the establishment of CLIFF | 1 in 2009/10 | 1 in 2010/11 | 1 in 2011/12 |  | GFDD Staff |
|  | ACTIVITY 2.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Produce and implement Annual CLIFF Business Plans and Budgets | Annually | Annually | Annually |  | GFDD Staff |
|  | ACTIVITY 2.4 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Communicate regularly with IPs, FCP and FPs, to discuss progress and fulfil contractual requirements under CLIFF | Regularly | Regularly | Regularly |  | GFDD Staff |
|  | ACTIVITY 2.5 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Complete visits to each IP at least every 6 months to support the monitoring and evaluation of progress (including fiduciary capacity), prepare Six-month and Annual Monitoring Reports, and distribute to CSB | Six-monthly | Six-monthly | Six-monthly |  | GFDD Staff |
|  | ACTIVITY 2.6 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Prepare Six-month and Annual Monitoring Reports for own activities and distribute to CSB | Six-monthly | Six-monthly | Six-monthly |  | GFDD Staff |
|  | ACTIVITY 2.7 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Draw-down funds from FCP, and disburse to IPs on a timely basis | As required, and at least on a quarterly basis | As required, and at least on a quarterly basis | As required, and at least on a quarterly basis |  | GFDD Staff |
|  | ACTIVITY 2.8 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Appraise Capital Grant Requests through own governance structures on a timely basis | As required | As required | As required |  | GFDD Staff |
|  | ACTIVITY 2.9 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Collect, quality control and monitor financial reports from IPs, and prepare and submit Quarterly Financial Reports to FCP | As required, and at least on a quarterly basis | As required, and at least on a quarterly basis | As required, and at least on a quarterly basis |  | GFDD Staff |
|  | ACTIVITY 2.10 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Submit annual external audits (for both the CLIFF project and the organisation) for IPs and CP to the FCP on a timely basis | Annually | Annually | Annually |  | GFDD Staff |
|  | ACTIVITY 2.11 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Provide and facilitate non-financial support for IPs where valuable where possible | Wherever possible and valuable | Wherever possible and valuable | Wherever possible and valuable |  | GFDD Staff |
|  | ACTIVITY 2.12 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Provide guarantees to help secure bank loans for CLIFF-supported projects as well as other relevant projects not supported by CLIFF where possible | Wherever possible and valuable | Wherever possible and valuable | Wherever possible and valuable |  | GFDD Staff |
|  | ACTIVITY 2.13 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Co-ordinate and support development and delivery of the Communications Strategy with FCP | Regularly | Regularly | Regularly |  | GFDD Staff |
|  | ACTIVITY 2.14 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Co-ordinate Mid-term and End of Project Evaluations | Mid-term Evaluation in 20011/12 | End of Project Evaluation in 20013/14 |  |  | GFDD Staff |
|  | ACTIVITY 2.15 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Co-ordinate RLP Events, in conjunction with the hosting IP, and participate | Annually | Annually | Annually |  | GFDD Staff |
|  | ACTIVITY 2.16 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Co-ordinate and support efforts to raise additional funding for CLIFF, if effective demand is demonstrated | As required | As required | As required |  | GFDD Staff |
|  | ACTIVITY 2.17 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Organise, act as Secretary to, and participate in CSB meetings | Six-monthly | Six-monthly | Six-monthly |  | GFDD Staff |
|  | ACTIVITY 2.18 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Report on CLIFF progress to own governance structures and ensure related decisions are made on a timely basis | Regularly | Regularly | Regularly |  | GFDD Staff |

| OUTPUTS 2-3 & 5-6 | ACTIVITY 3.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer |
| --- | --- | --- | --- | --- | --- | --- |
| Funding Channel Partner (FCP) | Produce and implement Annual CLIFF Business Plans and Budgets | Annually | Annually | Annually | The models developed and demonstrated through CLIFF may not be replicated at scale by others There may not be sufficient mobilisation, leverage and blending of resources from the public or private sectors Necessary pro-poor changes in policy and practice may not be stimulated by CLIFF demonstrations The emerging global financial crisis may limit CLIFF projects by constraining the availability of community, public and private resources | GFDD Staff |
|  | ACTIVITY 3.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Communicate regularly with IPs, CP, and FPs, to discuss progress and fulfil contractual requirements under CLIFF | Regularly | Regularly | Regularly |  | GFDD Staff |
|  | ACTIVITY 3.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Prepare Six-month and Annual Monitoring Reports for own activities and distribute to CSB | Six-monthly | Six-monthly | Six-monthly |  | GFDD Staff |
|  | ACTIVITY 3.4 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Draw-down funds from FPs, and disburse to CP on a timely basis | As required, and at least on a quarterly basis | As required, and at least on a quarterly basis | As required, and at least on a quarterly basis |  | GFDD Staff |
|  | ACTIVITY 3.5 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Provide and facilitate non-financial support for IPs where valuable and possible | Wherever possible and valuable | Wherever possible and valuable | Wherever possible and valuable |  | GFDD Staff |
|  | ACTIVITY 3.6 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Co-ordinate and support development and delivery of the Communications Strategy with CP | Regularly | Regularly | Regularly |  | GFDD Staff |
|  | ACTIVITY 3.7 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support Mid-term and End of Project evaluations | Mid-term Evaluation in 20011/12 | End of Project Evaluation in 20013/14 |  |  | GFDD Staff |
|  | ACTIVITY 3.8 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Participate in RLP Events | Annually | Annually | Annually |  | GFDD Staff |
|  | ACTIVITY 3.9 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support efforts to raise additional funding for CLIFF, if effective demand is demonstrated | As required | As required | As required |  | GFDD Staff |
|  | ACTIVITY 3.10 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Participate in CSB meetings | Six-monthly | Six-monthly | Six-monthly |  | GFDD Staff |
|  | ACTIVITY 3.11 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Report on CLIFF progress to own governance structures and ensure related decisions are made on a timely basis | Regularly | Regularly | Regularly |  | GFDD Staff |

| OUTPUTS 2-3 & 5-6 | ACTIVITY 4.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer |
| --- | --- | --- | --- | --- | --- | --- |
| Funding Partners (FPs) | Communicate as required with IPs, CP and FCP, to discuss progress | As required | As required | As required | The models developed and demonstrated through CLIFF may not be replicated at scale by others There may not be sufficient mobilisation, leverage and blending of resources from the public or private sectors Necessary pro-poor changes in policy and practice may not be stimulated by CLIFF demonstrations The emerging global financial crisis may limit CLIFF projects by constraining the availability of community, public and private resources | GFDD Staff |
|  | ACTIVITY 4.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Provide and facilitate non-financial support for IPs where valuable and possible | Wherever possible and valuable | Wherever possible and valuable | Wherever possible and valuable |  | GFDD Staff |
|  | ACTIVITY 4.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support development and delivery of the Communications Strategy | Regularly | Regularly | Regularly |  | GFDD Staff |
|  | ACTIVITY 4.4 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support Mid-term and End of Project Evaluations | Mid-term Evaluation in 20011/12 | End of Project Evaluation in 20013/14 |  |  | GFDD Staff |
|  | ACTIVITY 4.5 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Participate in RLP Events | Annually | Annually | Annually |  | GFDD Staff |
|  | ACTIVITY 4.6 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Support efforts to raise additional funding for CLIFF, if effective demand is demonstrated | As required | As required | As required |  | GFDD Staff |
|  | ACTIVITY 4.7 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Participate in CSB meetings | Six-monthly | Six-monthly | Six-monthly |  | GFDD Staff |

# Footnotes

The project will benefit the poor, and as far as possible the poorest and most vulnerable

Indian Alliance

Indian Alliance

Will take stock of governance and implementation and will ensure that the monitoring, data recording and reporting are fit for purpose. (by Sep 2011)

India

Further countries where DFID support is given will be aimed at Low Income Countries, particularly in Sub-Saharan Africa and South Asia

Such as those concluded within the 2008 CLIFF Evaluation, including: (1) Financial management and procurement; (2) Fund management; (3) Preparation, construction and post-construction management of projects; and (4) Governance

Indian Alliance

Relates to Indian Alliance only

Relates to Indian Alliance only

Broken down as follows: Indian Alliance (£0.2 million), Kenyan Alliance (£0.2 million) and Philippine Alliance (£0.5 million)

Broken down as follows: Indian Alliance (16.8), Kenyan Alliance (3.3) and Philippine Alliance (0.5)

Includes financial sustainability in terms of cost recovery (e.g. loan repayments) and longer term maintenance

To March 2009 Capital Grants were requested from Implementing Partners for complete housing units and on an ownership model only.  In the future, Capital Grants are expected to be requested from Implementing Partners for housing units constructed on an incremental basis as well as on a rental as well as ownership model

Broken down as follows: Indian Alliance (5,380), Kenyan Alliance (101) and Philippine Alliance (192)

Basic services are in addition to such facilities being provided as part of housing units

Relates to Indian Alliance only

Data to be gender disaggregated Estimated based on an assumed average family size of five

To March 2009 Capital Grants were requested from Implementing Partners for complete housing units and on an ownership model only.  In the future, Capital Grants are expected to be requested from Implementing Partners for housing units constructed on an incremental basis as well as on a rental as well as ownership model

Broken down as follows: Indian Alliance (26,900), Kenyan Alliance (205) and Philippine Alliance (960)

Data to be gender disaggregated, Estimated based on an assumed average family size of five

Basic services are in addition to such facilities being provided as part of housing units

Relates to Indian Alliance only

Logframe will be updated when Specific indicators are established with each IP as part of the Annual CLIFF Business Planning process

Logframe will be updated when Specific indicators are established with each IP as part of the Annual CLIFF Business Planning process and communication strategy

E.g. Financial institutions, academic and research institutions, and construction contractors, developers, professionals and material suppliers

Implementing Partners, Co-ordinating Partner, Funding Channel Partner and Funding Partners

E.g. Six-month Monitoring Visits, Fiduciary Monitoring Visits and Mid-term and End of Project Evaluations

E.g. Linking the CLIFF activities of IPs with potentially synergistic programmes, in particular those programmes being implemented by CP; Providing or facilitating access to financial services, such as loans and guarantees; and Supporting the development of IPs’ capacity, for example in the areas of strategic planning, financial management, procurement, project management, and engaging with the financial sector

E.g. Linking the CLIFF activities of IPs with potentially synergistic programmes, in particular those programmes being implemented by FCP; and Supporting the efforts of IPs to engage and influence relevant government departments to commit the resources and create the policy environment required to enable adequate and sustainable housing and basic services to be provided for slum dwellers at significant scale

E.g. Linking the CLIFF activities of IPs with potentially synergistic programmes, in particular those programmes being implemented by FPs; and Supporting the efforts of IPs to engage and influence relevant government departments to commit the resources and create the policy environment required to enable adequate and sustainable housing and basic services to be provided for slum dwellers at significant scale

# Comments

May change