Submission of Proposals: Application Form

Please read carefully the "Guidelines for the Submission of Proposals" which outline the modalities for application and the criteria for the selection of proposals spelled out in the Cities Alliance Charter. Please ensure that all necessary supporting documentation is attached to this form. Additional information may also be enclosed, but total submission should not exceed 12 pages.

DATE: 20 October 2011

1.  TITLE of PROPOSAL: Good Governance for Growth & Transformation- The State of Ethiopian Cities Project

2.  PROPOSAL SUBMITTED BY:

Name and Title:  Dr. Samson Kassahun, Academic Vice President

Organisation:  Ethiopian Civil Service University

Address:  P.O.Box: 5648 Addis Ababa, Ethiopia

Telephone/Fax/E-mail:  +251116463015 /+251116463016/ Samson.Kassahun@ECSU.edu.et

Contact person for questions on the application:

Name and Title:  Mr. Tilahun Fekade Director of the Institute of Urban Development Studies

Organisation: Ethiopian Civil Service University

Address:  P.O.Box: 5648 Addis Ababa, Ethiopia

Telephone/Fax/E-mail:  +251116463015/+251116463016/ tilahunddg@yahoo.com

3.  CITIES ALLIANCE MEMBER(S) SPONSORING THE APPLICATION:

Name and Title: Mr. Belay File, Head of Policy and Programme Bureau

Organisation: Ministry of Urban Development and Construction, Democratic Federal Republic of Ethiopia

Address:  P.O. Box 24134, Addis Ababa, Ethiopia

Telephone/Fax/E-mail:  251 (0)11 554 1261. Fax: 251 (0)11 554 1259/  belayfile@yahoo.com

Contact person for questions on the application:

Name and Title:  Alemakef Tassew, Senior Statistics and Research Expert

Organisation: Ministry of Urban Development and Construction

Address:  P.O. Box 24134, Addis Ababa, Ethiopia

Telephone/Fax/E-mail:  251 (0)11 554 1264. Fax: 251 (0)11 554 1259/ alemetassew@gmail.com

Name and Title: Abebaw Alemayehu, Senior Urban Specialist

Organisation: World Bank Mission to Ethiopia

Address: P.O. Box 5515, Addis Ababa, Ethiopia

Telephone/Fax/E-mail: +251 11 5176084/ 251-11-6627717/  aalemayehu@worldbank.org

Name and Title:Martin Dirr, Programme Coordinator  Urban Governance and Decentralisation Programme

Organisation:Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH

Address: P.O. Box 12631, Addis Ababa, Ethiopia

Telephone/Fax/E-mail: +251 (0) 11 518 0276/ +251 (0) 11 554 0768/ martin.dirr@giz.de

4.  RECIPIENT ORGANISATION: – organisation that will receive and execute the grant:

Name and Title:  Dr. Samson Kassahun, Academic Vice President

Organisation: Ethiopian Civil Service College

Address:  P.O.Box: 5648 Addis Ababa

Telephone/Fax/E-mail:  +251116463015 /+251116463016/ Samson.Kassahun@ECSU.edu.et

5.	OTHER IMPLEMENTING PARTIES (if any):

Task Manager Name & Title: Ntombini Marrengane, SOCA Project Coordinator

Organisation:   African Centre for Cities, University of Cape Town

Address:  PvtBag X3 Rondebosch 7701 South Africa

Telephone/Fax/E-mail:  +27-21-650-2881/ +27-86-519-6078/ cn.marrengane@uct.ac.za

INFORMATION ON PROPOSED PROJECT:

- Type of project(check one):

City Development Strategy_X_		Slum Upgrading__		    Both__

- Geographic scope of project(specify):

City:			_______

Country:		 Ethiopia

Global/Regional/Multi-country:	________

- Expected duration: 36 months

BUDGET SUMMARY:

- Amount of total budget requested from Cities Alliance funding: US Dollars 351,700

- Co-financing amount of total budget, including local partners: US Dollars 173,400

- Total project budget cost: US Dollars 525,100

DESCRIPTION OF PROPOSED PROJECT:

12.  Background –issues to be addressed and scope of project

Ethiopia is the second most populous country in the African continent. The 2007 Ethiopian Population and Housing Census showed that at least 12 million residents live in its urban centres and this number according to the UN will double by the year 2020 making Ethiopian urban populations amongst the second largest in the region surpassed only by Nigeria. Ethiopia human development indicators rank Ethiopia amongst the poorest countries of the world.  For example according to the Growth and Transformation Plan, 40% of the Ethiopian Urban population lives in slums with poor access to sanitation and other services.

These images stand in stark contrast to contemporary Ethiopia where in the last decade the nation has demonstrated consistent growth of 11% GDP placing it among the strongest economies of the continent. This growth has been a major lever which the government has used in order to address many of the poor human development indicators and specific challenges resulting from high population growth and insufficient access to infrastructure and other services.

In the last fifteen years as urban populations increased dramatically the Federal Democratic Republic of Ethiopia (FDRE) has designed and undertaken significant policy reform in order to achieve its national development goals of poverty reduction, improved access to basic services and effective governance for its citizens. Through the establishment of the Ministry of Works and Urban Development recently reorganized with additional responsibility as the Ministry of Urban Development and Construction (MUDC), the Government of Ethiopia (GOE) has recognised the importance of urban centres as engines of economic growth and rapid development. Building on the success of the Plan for Accelerated and Sustained Development to End Poverty (PASDEP) which enabled the Federal Democratic Republic of Ethiopia (FDRE) to achieve significant reductions in the number of households living in poverty, the GOE has recently announced its 5 year Growth and Transformation Plan (GTP) 2011-15 through which it plans to leverage the growth of cities for further national development. The objectives of the GTP include:

- projected average growth of the industrial sector of 21% per annum

- projected minimum overall economic growth of 11%

- extending  the coverage and quality of health and education services

- creating and strengthening a stable democratic and developmental government and

- supporting a conducive environment for the continuing national capacity building

The GTP also puts forward specific objectives for the urban sector aiming at reducing urban poverty and unemployment as well as strengthening the capacities and the governance system of cities. These objectives are:-

- to insure stronger urban local capacities to developed and manage urban infrastructure and services

- to deliver efficient, effective and fair infrastructure and services to urban citizens sustainably and

- to improve the urban environment for living and work.

By defining clear objectives and strategies for urban development the government has shown its commitment for healthy and balanced urban development as well as urban poverty reduction. Understanding the current state of Ethiopian cities and constant monitoring of progress towards the defined development targets are among the essential tasks of realizing the GTP objectives for urban development. While a range of analytical work has been completed on the public sector, more analytical work is required to measure progress achieved in urban areas across Ethiopia. As the nation continues to make strides towards poverty reduction, and increasing access to services, the productivity and sustainability of Ethiopian cities will depend upon:

- Consistent and regular collection of data based on urban realities that will support empirical decisions making by policy makers and officials at city and national levels

- Strategic analysis on the level of demand for services today as well as the need for the expansion of the services into the future as cities grow and change

- Capacity building opportunities at tertiary institutions based on experiential learning and research to enable the next generation of urban practitioners to grasp the evolving conditions in urban centers and

- Development of a network of urban practitioners and scholars for the purpose of sharing information lessons and challenges in order to achieve national development goals.

This state of cities report aims to support policy makers and local decision makers by providing analytical data on the existing patterns and profiles in Ethiopian cities that can be used to plan and measure progress into the future.  The State of Ethiopian Cities Report assembles and verifies existing data. It also collects new data on topics that are essential for the report but are not addressed by previous surveys and researches. In this senses the report creates a good synergy with the Integrated Urban Database activity supported by the Cities Alliance and hosted by the MUDC. Furthermore the first round report will provide a good base for launching the integrated urban database. The State of the Ethiopian Cities activity also provides an institutional base for the data and the project within a learning institution thereby ensuring that what is gathered will be used in training the next generation of scholars and practitioners in Ethiopian cities.

13.  Objectives

This proposal aims to mobilize resources to attain three specific objectives that will contribute directly to both its national development goals and enable city governments to address the service delivery needs of their residents. The first objective is to collect, analyze and disseminate data on the selected urban centres including the largest cities in the country.  The lack of up to date and well organized data on the largest and fastest growing urban centers of Ethiopia makes managing of urban growth challenging. The second objective is to utilize the process of collecting and analysing data on the major growth nodes across the country to engage with urban practitioners and scholars in Ethiopia. This approach signifies an important shift in urban research, knowledge production and dissemination methods undertaken in the past, by relying on local skills, expertise and knowledge on Ethiopian cities. The third objective is to use the process of compiling the State of Ethiopian Cities Report to enhance existing networks at federal, regional and local level to build a platform for professional exchanges, information sharing and policy feedback on urban management on a national and regional basis.

The proposed vehicle for this task is the State of Ethiopian Cities Project (SECP) which will form part of the larger State of the Cities in Africa – supported and hosted  by the African Centre for Cities (ACC) at the University of Cape Town.

14.  Methodology and sequencing of activities

The objectives of this proposal will be undertaken systematically in three components as outlined in the methodology section hereafter.

Methodology

The methodology for the SECP is based on two streams of activities;  one will be anchored at the ECSU on behalf of the MUDC and the second anchored at the ACC at the University of Cape Town. The ECSU will host the State of Ethiopian Cities Project under the direction and coordination of the MUDC. The Statistics and Research department of the MUDC will work closely with the ECSU and the SOCA Project team as the main partner of the project. The roles, responsibilities and obligation of MUDC and ECSU will be stated in a Memorandum of Agreement (MOA) to be signed by the both parties. The ECSU and MUDC will receive ongoing technical support from the SOCA Project team based at the African Centre for Cities which is supporting the preparation of State of the Cities Reports and capacity building activities in two other countries. This arrangement will enable the SECP team to benefit from the experiences and shared knowledge derived from the other country processes.

In Ethiopia, the implementation arrangements are based on the principle that the ECSU will act as a project management unit (PMU) with responsibility for the day to day management of the SECP on behalf of the Ministry of Urban Development and Construction. The ECSU will also serve as the host institution of the project with responsibility for management of financial and technical resources. Regular communication will be maintained between MUDC and ECSU throughout the project implementation period. The communication will take place in the form of reports and regularly scheduled Project Steering Committee (PSC) meetings. As the PMU, the ECSU will manage the design and implementation following components:

Component One: Assembling and Analyzing Data on the Current Urban System in Ethiopia

The first component of the (SECP) is the systematic collection of baseline data and analysis of data on urbanization in Ethiopia in the past 15 years.  A significant amount of analytical work has been done in the recent past that provides insight into the development and trajectory of urban centers in Ethiopia. In 2005, the GOE issued an urban policy that prioritized urban reform and capacity building with the public sector which served as a basis for restructuring programmes executed at the regional and urban levels. However to date, the available information is not organized, catalogued and analyzed in way that will assist proactive and pro-poor decision-making by city level stakeholders. The need for this type of information is increasingly vital, as the pace of investment across the nation accelerates and the GOE works to harmonize and align investment to ensure that there is pro-poor and equitable development across the nation. The outcome of this first activity will be a baseline report providing researchers and urban managers with a contemporary description of urban realities in terms of economic base and activities, service delivery level, infrastructure, population dynamics, governance structures and environmental situation and analyses. The aim of this report is to serve as a catalyst for strategic discussions on the trajectories of Ethiopian cities. It is anticipated that this first baseline report will inform and shape ongoing dialogue at city, regional and national levels on the growth of cities and their contribution to national development.

The preparation of the report will involve building on three important instruments developed by the GOE with the support of the World Bank and other development partners. The first instrument is the Annual Woreda City Benchmarking Survey (WCBS). The WCBS is a joint impact monitoring instrument of the GOE and its donors and in existence since 2005. The WCBS tracks the impacts achieved through the various capacity building and reform measure implemented by the GOE and its development partners.  Every year the WCBS increases its coverage of local urban and rural administrations with the objective of including all of them gradually.  The survey is repeated in similar cities and Woredas regularly to track progresses or setbacks.  The survey provides information on institutional capacity, service delivery, financial management, public participation and governance of Ethiopian cities. The WCBS compares supply and demand side information in each city thereby providing a good information base that will enable the State of Ethiopian Cities to reflect city performance and service from the community level as well as the administrative level.

The second instrument the State of the Ethiopian Cities Report can build on is the initiative of establishing a national municipal service standardization and performance measurement system launched by the MUDC. This system intends to generate reports on the level and quality of services provided by cities to their citizens as compared the service standards set.  As a national monitoring system producing annual data and reports it has a strong potential to strengthen the data source of the State of the Ethiopian Cities Report as far as the theme of municipal services is concerned.

The third instrument that is complementary to the state of the SECP is the Integrated Urban Database project being implemented by the MUDC and supported by the Cities Alliance.  While the preparation of the baseline  State of the Ethiopian Cities Report provides a good foundation for the Integrated Urban Data Base project, as an initiative deigned to broaden the information base of the urban sector in Ethiopia, the integrated urban database will be an important information base to the report in the long run. In addition the Statistics and Research Department of the MUDC and the information and statistical abstracts that will be produced by the department will be strong resources for the State of the Ethiopian Cities Report and vice versa.

Component Two: Building the Capacity of Urban Scholars and Practitioners

The second component of the SECP is based on using the preparation of the State of Ethiopian Cities Report as a vehicle to strengthen the capacity of Ethiopian scholars and practitioners through the production and exchange of knowledge on the urban sector. Various research has been completed on larger cities of Ethiopia. However, the data from these sources has not been well organised and disseminated to serve as a tool policy makers, regional and local decision makers and practitioners to the desired level. The SECP will improve on this by providing a platform to engage  local scholars and practitioners in the process of collecting and assembling city level data. Through the recruitment of research intern cohorts from the Ethiopian universities with urban and built environment programmes led by the ECSU, post graduate level scholars who are often also city officials will have the opportunity to be involved in the identification of data sources and compilation of city profiles to be used in the preparation of the first State of Ethiopian Cities Report. This opportunity will not only promote additional skills amongst university based post graduate students but the skills will be transferred into local authorities when the graduates return to their cities. In addition the work will enable practitioners to write and contribute empirical work based on their daily practice as urban specialists in the public and non-public sectors. The work will begin with a compilation of an annotated bibliography on urban development in Ethiopia since 1995 with particular attention to the research generated at tertiary institutions in Ethiopia as well as from external sources. This bibliography will serve as a foundation for the establishment of an urban resource centre to be located at the ECSU and provide a contemporary knowledge product on urbanisation in Ethiopia. The exercise of preparing the annotated bibliography will include the creation of a digital repository for urban research in Ethiopia available to ECSU and other regional universities. The bibliography will also be made accessible through the urban knowledge portal www.urbanafrica.net which services as knowledge platform on urbanisation on the African continent.

Component Three: Strengthening  Platforms for Urban Knowledge Networking and Exchange in Ethiopia

The third and final component of the SECP will comprise two elements. The first element is connecting urban practitioners at a technical level both inside and outside of public service starting with the compilation of the ECSU’s alumni list from its urban development training programmes in order to establish an urban practitioners network. It is anticipated that the network while being introduced at ECSU will expand to include graduates from other training institutions who go onto become urban practitioners in both public and private sectors This will include graduates from built environment and urban management training programmes at Addis Ababa University as well as  other regional training institutions outside of the capital.

The second element will entail engaging with other SOCA country teams on the continent  preparing State of the Cities Reports as well as developing linkages with countries in the global South which have undertaken similar processes. The ACC will organize sub-regional workshops to bring together SOCA country teams for both knowledge exchanges and technical support particularly in specialized areas such as data management and analysis. Furthermore the World Bank Institute has committed, through its South-South Learning Exchange Programme to support video-conference meetings between country based SOCA teams in order to share information, exchanges lessons learned and provide practical examples of how to implement this type of activity. There is already in operation a Global Development Learning Centre (GDLN) at the ECSU and resource is readily available to support knowledge exchange between the teams in Ethiopia and other parts of the world.

Building up on the results of component one and two the third component will strengthen experience exchange among Ethiopian scholars and practitioners working in areas of urban management and development on the basis of authentic and well researched urban data.  Academic institutions, associations, networks etc will serve as a vehicle for the dissemination of the State of the Ethiopian Cities Report through their platforms and networks. One of the partners of this initiative, the Ethiopian Cities Association is important in this regard to disseminate and use the information produced by the State of the Ethiopian Cities Report and the urban resource centre for policy/programme feedback and dialogue to be located at the ECSU.

15.  Deliverables

The following deliverables are anticipated from the implementation of the proposed activity:

Component One:

For component one there will be four main deliverables. The first deliverable is a detailed work plan for the preparation of the first State of Ethiopian Cities Report. The second deliverable will be a human resource plan and detailed corresponding budget for the rollout of the report. The third deliverable for component one will be a baseline report on the profiles of the urban centers identified by the MUDC and ECSU. The report will present both new data as well as synthesize existing data from various researches assembled on urban centers across the country. The report will provide a measuring point against which the GOE can track and manage the outcomes of its development plans. The fourth and final deliverable will be a dissemination strategy for the State of Ethiopian Cities report. The dissemination strategy of the State of the Ethiopian Cities Report include among others:

- Dissemination of the State of Ethiopian Cities Report and other related knowledge products through the Ethiopian Cities Association (experience exchange workshops, ECA website, thematic groups and publications)

- Forums and publications of the Ministry of Urban Development and Construction

- The Ethiopian Civil Service University (will be used as inputs for lectures and will be made available in libraries )

- Universities that are engaged in the urban management field

- GIZ urban governance and decentralisation programme and its regional and local architecture

- The urban development forum consultation platforms and

- Professional associations

The report is intended to serve as a catalyst for ongoing policy dialogues and assessments on the growth of urban centres in Ethiopia.

Component Two

For component two there will be three main deliverables. The first deliverable will be improved empirical research skills of urban practitioners. This will be achieved through process-oriented collection and analysis of urban information as well as by working closely with federal, regional and local government officials and local consultants to identify and analyze data on urban trends in select cities. The second deliverable will be the development of materials that can serve as reference in the adaptation and incorporation of the empirical research into the training curriculum at the ECSU and other regional training institutions across Ethiopia. The third and final deliverable will be the establishment and maintenance of an Urban Resource Centre based at the ECSU which provides access in hard copy or electronic format to analytical work completed in the course of the preparation of the baseline State of Ethiopian Cities Report. The centre will act as a repository for primary and secondary research and data related to growth of cities, building on and inclusive of the work completed by Ethiopian postgraduates on urbanization in both English and other local languages as may be appropriate. The urban resource centre will serve as a major instrument of enhancing the quality of urban research in Ethiopia by making authentic and well-researched data available for students, researchers and urban practitioners. The resource centre will also make a significant contribution in the development of new urban development related courses as well the revision of the existing ones. Thus, the centre will have a critical importance in upgrading the quality of education and services the ECSU offers. The centre will be a critical resource for postgraduate students based outside of the capital as well as in training institutions throughout the Africa region. Therefore the ECSU is committed to allocate annual budget and staff to manage, update and upgrade the urban resource centre that will be established under the auspices of the SECP.

Component Three

The final component in this proposal will produce two deliverables..  The first  deliverable is to support the strengthening of knowledge networking and information sharing amongst urban practitioners and scholars in Ethiopia. This will be accomplished in two ways. First through the establishment of an urban practitioner alumni network comprised of graduates of the ECSU and current practitioners in the member cities of the Ethiopian Cities Association and beyond. The alumni network will engage with the ECA to expand opportunities for knowledge sharing and exchange. The alumni association will actively contribute to the knowledge sharing by disseminating recent studies and data from local authorities to the Urban Resource Centre to be located at the ECSU.  This information repository will serve as an open resource to enhance the performance of urban practitioners and local government officials throughout the country in order to promote peer to peer learning and a community practice. The second deliverable will be ongoing contributions to the ACC based urbanafrica.net portal a web based platform for information exchange and dissemination on urban management research and practice in African cities. The added value that the SECP brings is that it will provide a vehicle through which to channel data and research for wide dissemination through the portal.

16.  Expected outcomes and related monitoring indicators and plans

| Component | Activity | Expected Outcomes | Indicator |
| --- | --- | --- | --- |
| One: Assembling and Analyzing Data on the Current Urban System in Ethiopia | - Identification of cities to be included in the SCR - Identification of themes for inclusion in the SCR - Development of TORS for core expert team and post-graduate scholars undertaking research and mining existing data for city level profiles - Preliminary scan of urban development research in Ethiopia - Validation of existing urban data - Collection of new baseline data for non-exiting/outdated information - State of Ethiopian Cities Report preparation | - Baseline State of Ethiopian Cities Report - Key Urban Development Actors of Ethiopia improved National, regional and local dialogue on urbanization in Ethiopia - Local decision makers have better access to information in order to make strategic decisions. | - Key urban development stakeholders confirmed that the State of Ethiopian Cities Report is a useful instrument to initiate and feed constructive urban dialogue in Ethiopia. b) Local decision makers find the information provided by the State of Ethiopian Cities useful to steer local development - Comprehensive dissemination strategy for the balseline State of Ethiopian Cities Report and its associated knowledge products developed in English and Amharic |
| Two Building the Capacity of Urban Scholars and Practitioners | - Recruitment of research teams to be deployed in each of the geographic regions covered in the report - Empirical research carried out by postgraduate students at ECSU and local government officials - City profiles reflecting current data on largest cities in Ethiopia - Creation of an urban resource centre with digital and hard copy resources available on urban development in Ethiopia | - Improved empirical research skills of ECSU postgraduate students. - City administrations use data from city profiles (prepared by urban scholars and practitioners) to inform local planning and decision making. | - Annotated bibliography complete and hard/ soft copies of the research collected and catalogued at the ECSU and posted on urbanafrica.net - The assessment result of postgraduate students on research methods improved compared to the previous year. - Urban Resource Centre established at |
| Three Strengthening of Knowledge Exchange and Networking | - Establishment of a nationwide urban practitioner network - Experience exchange and dissemination of best practices through publications and national urban practitioner network the Ethiopian Cities Association and other platforms | - The quality of national, regional and local urban development strategies improved through the growing body of knowledge on Ethiopian cities. - Technically driven practitioner network for urban managers in Ethiopia is created and linked with other networks throughout the sub-Saharan African region - Experience exchange and feedback at national, regional and federal level strengthened. | - Urban practitioner network created based on the ECSU alumni list - The State of Ethiopian Cities Report is disseminated through knowledge and information exchange platforms to relevant stakeholders - Regular contributions to urbanafrica.net knowledge portal |

17. Sources of investment to implement the CDS or slum upgrading programme

Since 2008the World Bank has committed USD $150 million towards the Urban Local Government Development Programme (ULGDP).  The World Bank financing is matched by 40% (USD$ 60 million) combined self-contribution of regional Bureaus and Cities along with  additional financing of USD $150 million has been recently approved to extend the reforms of the Urban Local Government Development Programme to more cities. The extension grant is conditioned to similar matching fund criteria.   In addition to fostering infrastructure development and strengthening management capacities on local levels, ULGDP encourages the participation of urban citizens in identifying priority capital investment projects and in urban planning.

Another financing instrument available for the less developed cities of Ethiopia is the 10 million Euro infrastructure grant provided by the German Development Bank (KfW). This KfW grant is matched by a technical cooperation support of GIZ worth 5 million euro.  Capital cities of the emerging regions as well as small and medium size cities are beneficiaries of the German Development Cooperation support. Additionally, through the 2nd phase of the “Public Sector Capacity Building Programme” (PSCAP) financing is available for regional governments and cities.

18.  Partnerships

Strong partnerships with the bilateral and multilateral donor community anchor the proposed support to the GOE and the ECSU for the preparation of the first State of Ethiopian Cities Report. This proposed activity is well aligned to the World Bank Country Assistance Strategy for Ethiopia 2007-2011 which aims to support the following objectives: (i) fostering economic growth; (ii) improving access to and quality of basic service delivery; and (iv) fostering improved governance. These objectives are in synch  with the proposal for the State of the Cities Report as the process of compiling the report is aimed at an enhancing the ability of GOE to attain the above development goals.

The proposed activities are also linked with the German Technical Cooperation agency, recently renamed GIZ, through its urban governance and decentralisation programme (UGDP). Since 1995 German development agencies have supported the GOE in developing and implementing programmes for sustainable development. The current programme of support focuses on three core areas closely aligned to the objectives of this proposal; namely capacity building for sustainable economic growth; improved urban governance linked to a systematic programme of decentralization and improved food security. The work programme of the GIZ in the area of urban development focuses on three areas central to the proposed activity namely:

- improving urban financial management

- improving urban planning

- Improving urban infrastructure provision and management

- Strengthening knowledge management and the facilitating exchanges between cities.

The Ethiopian Cities Association (ECA), a membership based organization of the largest 28 cities in the country supports the proposed activity. The association has a strong interest in the SECP and intends to use the report as a platform in conjunction with other urban reforms and initiatives to engage its members on ways to improve urban development in Ethiopian cities.

As a formal association of Ethiopian cities and representing cities that are addressed by the project the Ethiopian Cities Association (ECA) plays a significant role in articulating the interest of its members in the design and implementation of the project. ECA offers platforms that will enable cities actively engage in project design and implementation. Furthermore the ECA will serve as one of the main instruments for the dissemination of the State of the Ethiopian Cities Report.  In the course of the project implementation the ECA will play a role in facilitating experience exchange platforms among the cities targeted by this project. After the production of the State of the Ethiopian Cities Report the ECA will:-

- facilitate the transfer of successful experiences that are identified in the city profiles among its member cities.

- use the main findings of the State of the Ethiopian  Cities report  to form and substantiate the agenda of its annual feedback forum of cities to federal and regional policy and programme makers

- contribute to the capacity development of Ethiopian urban practitioners by disseminating the report through its thematic working groups (the thematic working groups are among ECA instruments that are being developed to develop of customised tools and solutions for development challenges of ECA member cities. The groups are composed from urban practitioners based in various cities and institutions in Ethiopia).

19. Government commitment and approval

The Ministry of Urban Development and Construction fully supports the preparation of the first State of Ethiopian Cities Report. The MUDC has delegated the ECSU to manage and implement on its behalf the preparation, coordination and publication of the SECR. The MUDC will closely follow  both the process and product of SECR and is strongly committed to use the outcome. Furthermore, the MUDC also actively contributes to the project through steering, management and coordination of the project.

IMPLEMENTATION AND FINANCING PLANS:

- Implementation arrangements

The institutional arrangements for SOCA Project-Ethiopia will include a PMU, a Project Steering Committee and a Reference Group as detailed below:

SOCA Ethiopia Project Management Unit

The PMU will be situated in the Institute of Urban Development Studies (IUDS) at the ECSU. The staff compliment of the PMU will include a full-time national project coordinator, a finance officer and a project administrator. This team will report to and work closely with the Project Steering Committee to meet all the project goals which will be worked out in detail in MOU to be signed between ECSU and MUDC. The ACC and ECSU will support the PMU to meet its reporting and funding requirements in the execution of the project. This will include but not be limited to:

- Recruitment and management of project consultants;

- Selection and management of post graduate interns for research grant activities;

- Management of project documents and reporting to the steering committee as well as donors;

- Organisation and documentation of workshops and consultative meetings;

- Creation and maintenance of a  database containing contacts  of key stakeholders, researchers, consultants and local government partners;

- Acquisition and organisation of a photo and map library on cities for the report;

- Support the incorporation of project research and findings into the curricula for the Masters in Urban Management and the forthcoming academic urban programmes at the ECSU;

- Development of an urban resource centre at the ECSU.

The ECSU will manage relationships with the main stakeholders and ensure accountability to the MUDC. A memorandum of understanding will be signed between MUDC and ECSU to govern the implementation of the project.

Project Steering Committee:

The Project Steering Committee (PSC) will be composed of the following key stakeholders:

- Ministry of Urban Development and Construction (MUDC)

- Ethiopian Civil Service University  (ECSU)

- Ethiopian Cities

- Association World Bank

- Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH(GIZ)

- African Centre for Cities at the University of Cape Town (ACC)

The above members of the steering committee will guide and supervise the execution of the grant for the first Ethiopian State of the Cities Report and urban research on Ethiopia during the life of the grant.  Each member of the steering committee in addition to guiding the implementation of the project will be expected to contribute resources either in cash or in kind towards the funding of the proposed activity. Contributions may take the form of either in-kind assistance such as, staff time, office space, data on cities identified for the SOCA Project or cash.

Reference Group

A reference group will be established to provide an organised support in the area of urban and local government to provide constructive reflection and critique in order to strengthen the quality of the process and its anticipated deliverables. It is anticipated that the reference group will be composed of experts with technical knowledge of the themes to be researched as part of the first State of the Ethiopian Cities Report; these include but are not limited to:

- Relevant departments in the MUDC such as the:-

  - Policy and programme bureau

  - Statistics and research department

  - Urban good governance capacity building bureau

  - Urban planning sanitation and beatification bureau

  - land management and development bureau

  - Federal Micro and small scale enterprises Development Agency

- Regional bureau of urban development

- Regional Urban Planning Institutes

- Ethiopian Mapping Agency

- Central Statistical Agency

- Urban Development Forum of the Consortium of Christian Relief and Development Agencies (CCRDA)

- Institute of Local and Regional Development Studies, Addis Ababa University

Strong cooperation with regional bureaus of urban development will be formed to solicit their support in collecting, assembling and verifying data and in disseminating the report.  In addition, the PMU with the guidance of the MUDC will work closely with the regional bureau and city leadership in each of the cities to collate existing data, work with ECSU scholars to collect data not yet assembled on a regular basis to feature in the first State of Ethiopian Cities Report.

On a broader scale the project will work closely with existing urban development programmes in Ethiopia. The World Bank supported Urban Local Government Development Programme (ULGDP), the GIZ supported Urban Governance and Decentralisation Programme (UGDP), the Integrated Urban Database project managed by the Ministry of Urban Development and Construction (MUDC) and the Ethiopian Cities Association (ECA) are among the major urban development initiatives the project will collaborate with.  The instruments for cooperation with these programmes and partners are the project steering committee and the project reference groups.

The above mentioned programmes and partners will benefit from the State of the Ethiopian Cities Project by getting access to well researched and authentic data about the development situation of Ethiopian cities that can be used inputs for programme design and monitoring.  Furthermore At the same time they will contribute to the project by contributing ideas and resources to the project design, implementation and management.  They will also supply data to the envisaged urban resource centre. Capacity development of urban practitioners is also one of the central objectives of the project as well as the on-going urban development programmes and partners mentioned above.

Public Consultations

Another key element of project implementation will include a series of planned public consultations events to gather feedback on the development of the first State of Ethiopian Cities Report.  The following are major consultation mechanisms the project put forward:

The Ethiopian Cities Association (ECA): The ECA is the major consultation mechanism of the project addressing cities targeted by the project as well as relevant federal and regional bodies.  The ECA will offer its knowledge exchange and consultation platforms to enable cities discuss on the project design and implementation as well as preliminary results. Furthermore the ECA will serve as a dissemination mechanism for the various project outputs and their consumption by cities. As part of the project steering committee the ECA will represent the interest of its member cities in the management and implementation of the project. This will include the Ethiopian Cities Week, an annual platform of Ethiopian cities, urban development stakeholders and partners and the general urban public hosted by the ECA. The Ethiopian Cities Week offers an excellent platform to hold consultations on the objectives, processes and results of the SECP with cities and wider stakeholders.

Professional Associations: SECP will be engaged in regular dialogue with professional associations such as the Ethiopian urban planners associations, architects association and contractors association to incorporate the views of these stakeholders in the project and to disseminate its products.

The Urban Development Forum (UDF): The project will use the Urban Development Forum that is established under the Consortium of Christian Relief Development Associations (an umbrella organisation of NGOs and Associations operating in Ethiopia) as another mechanism to foster consultation on the State of the Ethiopian Cities Report. The UDF has regular discussion forums with urban development actors at various levels. These forums can be used to pursue consultation with members of the UDF.

- Project schedule and delivery targets

|  |  |  |  | 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2013 |  |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task/Month |  | M |  |  | A | M |  | J |  | J | A |  | S |  | O | N | D |  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M |
| Component 1: Assembly and Analysis of Data on Ethiopian Urban System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruitment of project coordinator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruitment of PMU staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of annual work plan & preparation of consultant TORS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop templates and formats for research inputs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scan of Ethiopian literature on Urban Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commission regional research teams and statistical experts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Collection and Mining |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Obtain photographs and maps of selected cities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submission of drafts city profiles for review and comment steering and editorial committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organise and host first national consultative workshop on ESCR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organise second workshop to review draft with steering committee & reference group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development and translation of policy briefs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit final report and briefs for layout to the graphic design team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit complete report to printer (1000 copies) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organise launch of first report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Building the Capacity of Urban Scholars and Practitioners |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organise and host regional workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrate post grads into data collection at city level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish urban resource centre at ECSU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish Urban Practitioner Alumni Network |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Incorporate research material into teach curricula at ECSU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Strengthening Platforms for Knowledge Exchange |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participate in ACC networking event to present findings to other SCR teams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit material for posting on urbanafrica.net |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

22. Cities Alliance Financing plan

| Components/Main Activities | Consulting Services (US $) | Training/Capacity Building (US $) | Dissemination Costs (US$) | Other (US$) | Total (US$) | Total Cost in Ethiopian Birr |
| --- | --- | --- | --- | --- | --- | --- |
| - Cities Alliance Request |  |  |  |  |  |  |
| Component #1 Assembling and Analysing Data on Ethiopian Urban Systems | 221,700 | 20,000 | 9,000 | 0 | 250,700 | 4,349,645 |
| Component # 2 Building the capacity of Urban Scholars and practitioners | 20,000 | 22,000 | 15,000 | 0 | 57,000 | 988,950 |
| Component #3 Building Knowledge networks | 2,000 | 12,000 | 10,000 | 0 | 24,000 | 416,400 |
| Sub-Total-Project Activities | 243,700 | 54,000 | 34,000 | 0 | 331,700 | 5,754,995 |
| Project Administration and Supervision |  |  |  |  |  |  |
| Independent Audit (1) | 5000 | 0 | 0 | 0 | 5,000 | 86750 |
| Supervision costs (2) | 0 | 0 | 0 | 15000 | 15000 | 0 |
| Sub-Total-Project Administration & Supervision | 5000 |  | 0 | 15000 | 20,000 | 86750 |
| Total A (Cities Alliance Financing) | 248,700 | 54,000 | 34,000 | 15000 | 351,700 | 6,101,995 |
| Co-Financing- B |  |  |  |  |  |  |
| Co-Financing Partner #1 ECSU | 15000 | 0 | 5,000 | 5,000 | 25,000 | 433,750 |
| Co financing MUDC | 10000 | 5,000 | 5,000 | 0 | 20,000 | 347,000 |
| Co-Financing Partner # 2-ACC | 30,000 | 5,000 | 10,000 | 5000 | 50,000 | 867,500 |
| Co-Financing Partner #3 –World Bank Institute | 25,400 | 0 | 3000 | 0 | 28,400 | 492,740 |
| Co-Financing Partner #4 - GIZ | 45,000 | 3000 | 2,000 | 0 | 50,000 | 867,500 |
| Total B (Co financing) | 125,400 | 13,000 | 25,000 | 10,000 | 173,400 | 3,008,490 |
| C. TOTAL | 374,100 | 67,000 | 59,000 | 25,000 | 525,100 | 9,110,485 |

See Guidelines for more information.

(1)  An external audit is required upon completion or termination of project activities.  Categories this type of expenditure as “other.”

(2)  Incremental costs associated with the management of the project, up to a maximum of 15 percent of the Cities Alliance grant request. Categorize this type of expenditure as “other.” Detailed cost break down required in Section 23 Costing Assumptions

23. Costing assumptions Provide details about the assumptions that were used to calculate the costs presented in the summary financing plan (22).

| Item |  | Unit (No./Days) |  | Rate in USD |  | Total in USD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Consulting Services |  |  |  |  |  |  |  |
| Project Manager |  | 250 |  | 180 |  | 45000 |  |
| Deputy Project Manager |  | 250 |  | 160 |  | 40000 |  |
| Project Administrator |  | 220 |  | 110 |  | 24200 |  |
| Project Finance Officer |  | 250 |  | 120 |  | 30000 |  |
| Statistician |  | 100 |  | 200 |  | 20000 |  |
| Urban economist |  | 100 |  | 200 |  | 20000 |  |
| Anthropologist / Sociologist |  | 50 |  | 200 |  | 10000 |  |
| Historian |  | 50 |  | 180 |  | 9000 |  |
| Urban Planner |  | 100 |  | 200 |  | 20000 |  |
| Housing Specialist |  | 100 |  | 300 |  | 30000 |  |
| GIS Specialist |  | 70 |  | 200 |  | 14000 |  |
| Engineer |  | 70 |  | 300 |  | 21000 |  |
| Transport Specialist |  | 70 |  | 200 |  | 14000 |  |
| Regional advisors |  | 30 |  | 200 |  | 6000 |  |
| National consultation facilitators |  | 5 |  | 120 |  | 600 |  |
| National consultation rapporteurs X 2 @100 per day |  | 5 |  | 100 |  | 500 |  |
| Research interns/ Post Grad Students (27 people at 20 days each-1 student per city) |  | 540 |  | 75 |  | 40500 |  |
| Editor |  | 100 |  | 200 |  | 20000 |  |
| Photographer |  | 15 |  | 120 |  | 1800 |  |
| Translators (2 at 25 days each) |  | 50 |  | 150 |  | 7500 |  |
| Total: Consulting Services |  |  |  |  |  | 374,100 |  |
| 2. Training/Capacity Building |  |  |  |  |  |  |  |
| * Establishment and maintenance of an Urban Resource Centre |  | 3 |  | 2,000 |  | 6000 |  |
| **Procurement of computers (workstations for country Project team) |  | 1 |  | 5800 |  | 5800 |  |
| Video-conference meetings between country based SOCA task teams @ $200 per site for 5 sites at least times per year |  | 6 |  | 1000 |  | 6000 |  |
| Travel expenses of national project team based on an estimate of $400 per round trip and 55 round trips from Addis Ababa over 24 months |  | 55 |  | 400 |  | 22,000 |  |
| ***Hotel and perdiems for the national project team estimated at US$50 per day at an average of 4 days per city |  | 136 |  | 200 |  | 27200 |  |
| Total Training/Capacity Building Costs |  |  |  |  |  | 67,000 |  |
| 3 Dissemination Costs |  |  |  |  |  |  |  |
| National consultative workshop on ESCR |  | 1 |  | 10000 |  | 10000 |  |
| Regional workshops |  | 8 |  | 875 |  | 7000 |  |
| Mid-term review workshops |  | 2 |  | 1500 |  | 3,000 |  |
| Graphics design, website and PR costs @400 per day |  | 30 |  | 300 |  | 9,000 |  |
| Printing |  | 500 |  | 40 |  | 20,000 |  |
| Launching event (venue and catering) |  | 1 |  | 10000 |  | 10,000 |  |
| Total Dissemination Costs |  |  |  |  |  | 59,000 |  |
| 4. Other |  |  |  |  |  |  |  |
| Independent audit |  | 1 |  | 5000 |  | 5000 |  |
| Administrative and supervision costs over the life of the project (monitoring, telecommunications & office sundry) |  | 1 |  | 20,000 |  | 20000 |  |
| Total other costs |  |  |  |  |  | 25,000 |  |
| GRAND TOTAL |  |  |  |  |  | 525,100 |  |
| * A physical space has already been allocated by ESCU for the resource centre, and a staff member dedicated to it, therefore the funds allocated are one off costs. |  |  |  |  |  |  |  |
| ** This once off cost is for computers X 2 @ 2000 each + $800 for printer + $1000 for toner |  |  |  |  |  |  |  |
| ** *The per diem is for consultants travelling outside the capital. Post grads returning to their home city will not be paid per diem but will be paid for days worked and travel. |  |  |  |  |  |  |  |

24. Expected currency of expenditures

Into what currency (or currencies) do you expect the grant funding (provided in U.S. dollars) to be converted? - Ethiopian Birr (ETB)

The grant will be converted into Ethiopian Birr. The current exchange rate is US1:ETB 17.35 as of March 2012.

What exchange rate assumptions have you used?  - Official exchange rates issues by the Commercial Bank of Ethiopia as of 9 March 2012.

25. Co-financing arrangements

| Co-financing Source | Description of Co-Financing |
| --- | --- |
| 1.MUDC | Management and coordination, Staff time, office space and equipment |
| 2.ACC | Cash to be made available to support implementation as well as staff time of an ACC based Editor in Chief and Data Specialist |
| 3.World Bank Institute | Cash to be made available to support South-South learning through the GDLN facility |
| 4. GIZ | 2 x 15 working days in 8 regions (incl. Travel costs); Office running costs for 15 working days in 8 regions; support of the federal team |

Is all co-financing confirmed/committed?  YES

26.  Additional Financial Management Information from Recipient

  - Is the Recipient a registered organization under the countries/cities legal requirement? –Yes

  - Can the recipient provide proof of registration and years of operation?	-Yes

  - Does the recipient have prior experience managing other Donor funds and provide documentation to support this - Yes

  - Does the recipient have or can open a bank account?-	Yes

  - Is the recipient audited annually?	-	Yes

  - Do you produce periodic financial reports for monitoring and evaluation?	(Yes/No)

Annex One: Proposed Themes for the State of Ethiopian Cities Report (to be refined at as part of Memorandum of Agreement between the MUDC and the ECSU)

- Economic Lives of Cities

- job creation

- Challenges and opportunities of the construction sector micro and small enterprises –best practices

- Support  for small enterprises, the experience of the past 5 years in selected towns with specific focus on skills development  measures, linkage with  microfinance, and facilitating  access to market

- Urban Land Management and Development

  - Integrated land management system

  - land and land related property registration of cadastre system

  - street address system

  - urban land management regularisation in Ethiopian cities

3, Urban Planning Practices and Sustainable Development

3.1 Plan Preparation

- Structural plan

- Local development plan

- Urban design

3.2 Urban Planning Current Practices and Challenges

- Status

- Challenges

- Prospects

3.3 Urban Environment

- green and open spaces in urban centres – waste management and sanitation

4. Population Dynamics in Cities

- Urban-rural linkages

- Growth corridors

- Migration

- Demographic profile of Ethiopian cities

5. Access to Urban Services

- shortage of finances for urban infrastructure projects

- housing, there is a shortage and a linked problem is the proliferation of slums both of these issues are to be addressed through the government housing programme

- urban infrastructure some of which are managed by parastatal agencies not necessarily under the direction of the MUDC as well as infrastructure at municipal level such as abattoirs, roads, drainage networks

6. Good Governance and Organisational Performance

- good governance linked to service delivery, providing services to urban residents

- gender to be mainstreamed in all aspects of urban development

- Building Capacity to Enhance Public Sector Performance

7. Urban Business Environment

- local  business and revenue bases

- Legal framework, tax laws governing the urban business

- Services provided by City administrations to boost business performance

Country-specific proposals typically originate from local authorities, but must be sponsored by at least one member of the Cities Alliance (see Cities Alliance Charter, Section D.14).